## Ark 1
| Plan |  |  |  |  | Design |  |  |  |  | Development |  |  |  |  | Launch
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Project meeting with customer | Customer contact, contract, project planning, proposal |  |  |  |  | Customer contact, contract, project planning, proposal |  |  |  |  | Customer contact, contract, project planning, proposal |  |  |  |  | Customer contact, contract, project planning, proposal
Project planning with the team |  |  | Planning and walk trough | [11 empty] | Walk through
Content creater and designer |  |  |  | Research
Designer |  |  |  |  | Wireframe | Styletile
Content creator and copywriter | [5 empty] | Text planning |  | Text writing
Photographer | [7 empty] | Portfolio and employee images
Developer | [10 empty] | Coding and Site building | [5 empty] | Cross browser testing |  | Validating
Content Creater and Designer | [11 empty] | UX/UI planning and testing |  |  |  | UX/UI testing
Project manager, designer, developer and content creator | [19 empty] | Launch